## Sheet1
| Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Week 1 | 5 hrs - Watched intro videos and started watching week 1 videos, completed software setup, and completed activities 1 - 5 | 1.5 hrs - Continued watching the Week 1 videos |  | 2 hrs - Watched the Exercise 1 video and started working on Exercise 1. Created the database and user table. Removed the first TODO and ran tomcat. | 3 hrs - Continued working on the TODO's for exercise 1. Worked on figuring out how to calculate the age as well as prettying up the table. Tried using JSTL to create a nice table for the user data with no luck. | 3 hrs - Continued working on Week 1 Exercise 1. Had to figure out issue with Intellij not being able to resolve the JSTL taglib | 2 hrs - Figured out issues with age calculation and got the Search functionality working. Turned in Week 1 Exercise 1 screenshots.
Week 2 | 4 hrs - Began watching week 2 video's. Began working on week 2 activities. | 2.5 hrs - Continued watching week 3 video's | 2 hrs - Finished watching week 3 video's and completed remaining week 2 activities | 2.5 hrs - Began week 3 readings. Began working on Week 2 Exercise 1 | 2 hrs- Continued week 3 readings and continued working on week 2 exercise 1 | 2 hrs- Continued working on week 2 exercise 1 | 2 hrs- Completed week 2 exercise 1
Week 3 | 3.5 hrs - Began watching week 3 video's and walking through the activity along with the video's | 2 hrs - finished watching week 3 video's and started working on week 3 Exercise assignment. | 3 hrs - Finished week 3 exercise and began looking at the different pieces due for the Individual project |  | 2 hrs - Began creating the Problem statement, project plan, and started planning the screens fo the individual project | 2 hrs -Finished creating the Problem statement and project plan. Also started creating the screens using Balsamiq. Tried moving the week 3 exercise to Github, but had issues. | 2 hrs - Finished creating the screens using Balsamiq. Again tried moving the week 3 exercise to Github, but had issues.
Week 4 | 4 hrs - After talking with Paula, figured out how to submit the week 3 exercise to github. Began watching the Week 4 video's and walking through the Hibernate Demo. |  | 1.5 hrs - Continued watching the week 4 video's and working through the Hibernate Demo | 2 hrs - Continued watching week 4 video's and working through Hibernate Demo | 2 hrs - Continued watching week 4 video's and working through Hibernate Demo | 2.5 hrs- Began adding the Hiker Account table and hibernate setups for the Week 4 Exercise 1 | 2 hrs - Finished setting up hibernate for my individual project hiker account table
Week 5 | 4 hrs - Began watching week 5 video's |  | 2 hrs - Continued watching week 5 video's and began working on the week 5 Demo |  | 2 hrs - Completed the Week 5 Demo and corresponding video's | 2.5 hrs - Began working on the week 5 exercise to add the one to many table to my individual project | 3 hrs - Finished adding the one to many table to my individual project and added the jUnit tests. Worked on resolving an error when running the jUnit tests.
Week 6 | 4 hrs - Listen to reviews of Individual projects. Began setup of AWS. |  | 1 hr - Began setting up the Login .jsp |  | 3.5 hrs - Perform code reviews for Sasha and Kyle. Looked at how bootstrap works and how to add it to my .jsp's.
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
Week 15
Week 16