## Sheet1
| Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Week 1 | 5 hrs - Watched intro videos and started watching week 1 videos, completed software setup, and completed activities 1 - 5 | 1.5 hrs - Continued watching the Week 1 videos |  | 2 hrs - Watched the Exercise 1 video and started working on Exercise 1. Created the database and user table. Removed the first TODO and ran tomcat. | 3 hrs - Continued working on the TODO's for exercise 1. Worked on figuring out how to calculate the age as well as prettying up the table. Tried using JSTL to create a nice table for the user data with no luck. | 3 hrs - Continued working on Week 1 Exercise 1. Had to figure out issue with Intellij not being able to resolve the JSTL taglib | 2 hrs - Figured out issues with age calculation and got the Search functionality working. Turned in Week 1 Exercise 1 screenshots.
Week 2 | 4 hrs - Began watching week 2 video's. Began working on week 2 activities. | 2.5 hrs - Continued watching week 3 video's | 2 hrs - Finished watching week 3 video's and completed remaining week 2 activities | 2.5 hrs - Began week 3 readings. Began working on Week 2 Exercise 1 | 2 hrs- Continued week 3 readings and continued working on week 2 exercise 1 | 2 hrs- Continued working on week 2 exercise 1 | 2 hrs- Completed week 2 exercise 1
Week 3 | 3.5 hrs - Began watching week 3 video's and walking through the activity along with the video's | 2 hrs - finished watching week 3 video's and started working on week 3 Exercise assignment. | 3 hrs - Finished week 3 exercise and began looking at the different pieces due for the Individual project |  | 2 hrs - Began creating the Problem statement, project plan, and started planning the screens fo the individual project | 2 hrs -Finished creating the Problem statement and project plan. Also started creating the screens using Balsamiq. Tried moving the week 3 exercise to Github, but had issues. | 2 hrs - Finished creating the screens using Balsamiq. Again tried moving the week 3 exercise to Github, but had issues.
Week 4 | 4 hrs - After talking with Paula, figured out how to submit the week 3 exercise to github. Began watching the Week 4 video's and walking through the Hibernate Demo. |  | 1.5 hrs - Continued watching the week 4 video's and working through the Hibernate Demo | 2 hrs - Continued watching week 4 video's and working through Hibernate Demo | 2 hrs - Continued watching week 4 video's and working through Hibernate Demo | 2.5 hrs- Began adding the Hiker Account table and hibernate setups for the Week 4 Exercise 1 | 2 hrs - Finished setting up hibernate for my individual project hiker account table
Week 5 | 4 hrs - Began watching week 5 video's |  | 2 hrs - Continued watching week 5 video's and began working on the week 5 Demo |  | 2 hrs - Completed the Week 5 Demo and corresponding video's | 2.5 hrs - Began working on the week 5 exercise to add the one to many table to my individual project | 3 hrs - Finished adding the one to many table to my individual project and added the jUnit tests. Worked on resolving an error when running the jUnit tests.
Week 6 | 4 hrs - Listen to reviews of Individual projects. Began setup of AWS. |  | 1 hr - Began setting up the Login .jsp |  | 3.5 hrs - Perform code reviews for Sasha and Kyle. Looked at how bootstrap works and how to add it to my .jsp's. | 2 hrs - continued setup of AWS | 2 hrs - continued setup of AWS
Week 7 | 4 hrs - Continued working through bugs for the setup of AWS | 3 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 3 hrs - Began putting together the slide show for my Professional presentation. Began creating the Generic Dao for my project. 3 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 3 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 2.5 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 2.5 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 2.5 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database.
Week 8 | 2.5 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 2.5 hrs - Continued trying to resolve issue with a 500 exception that won't allow my application to search the database. | 2.5 hrs - Resolved the issue with the 500 error and continued pushing my project to AWS | 2 hrs - began working on my Agile presentation. | 2.5 - Continued working on my Agile presentation. | 2.5 hrs - Continued working on my Agile presentation and began watching the Week 8 video's and began walking through Activity 1. | 2.5 hrs - Continued watching the Week 8 video's and began walking through Activity 2 and Activity 3.
Week 9 | 4 hrs - Gave my Agile presentation and continued working on the Week 8 Activities | 2.5 hrs - Continued working on Activity 3 to get the SOAP API test working. | 2 hrs - Completed the Week 8 SOAP API assignment and turned it in. | 1.5 hrs - Continued working on my indie project | 3 hrs - Continued working on my indie project. Worked on getting .jsp's created for Check point 3
Week 10 | 3 - Met for the first time with the team and decided to create an Event Service. Began talking through what types of end points we'd like this service to have. |  | 2 hrs - worked through the week 9 Demo/Exercise to get an idea of how Restful services work | 2 hrs - continued working through the week 9 Demo/Exercise to get an idea of how Restful services work | 2 hrs - began adding the Event Service to the team project. Created the Search end point and tried testing it | 3 hrs - continued testing the search endpoint and added the Add and Delete endpoints. | 3 hrs - finished the week 9 Restful service exercise and continued testing the Event service team project
Week 11 | 3.5 hrs - Worked with Steve and Kia to get the Event Services working correctly with the Dao and .jsp's | 3 hrs - continued working on the Event Service to get the search working correctly and get the add and delete working successfully | 3 hrs - continued working on the Event Service to get the search working correctly | 3 hrs - continued working on the Event Service to add and delete working successfully | 3 hrs - met with Steve and Kia to clean up our code and get everything pushed to github 3 hrs - continued working on the Event Service to get the search working correctly so that it only brings back rows for a specific date range | 3 hrs - continued working on the Event Service to get the search working correctly so that it only brings back rows for a specific date range | 4 hrs - finished cleaning up the Event Service code and making sure all of the output looks correct and everything is working correctly
Week 12 | 2 hrs - Give Event Service presentation in class and listen to other presentations |  |  |  | 2 hrs - Filled out Team project survey. Worked on getting back up to speed on indie project | 2.5 hrs - Worked on creating the Hiking Trails jsp | 2.5 hrs - worked on the week 13 exercise
Week 13 | 1.5 hrs - worked on the week 13 exercise 3 hrs - worked on getting user authentication working for my indie project | 2 hrs - continued working on getting authentication working for the indie project |  | 3 hrs - Worked on trying to get tabs to work for the menu options of my indie project | 3 hrs - Worked on trying to get tabs to work for the menu options of my indie project | 3.5 hrs - Worked on getting the Add Trails .jsp and the Login .jsp formatted correctly and working | 3.5 hrs - Worked on getting the Add Trails .jsp and the Login .jsp formatted correctly and working
Week 14 | 4 hrs - Worked on getting my Search page working correctly. | 3 hrs - Worked on getting my Search page working correctly. | 3 hrs - Worked on getting my Search page working correctly. | 3 hrs - Worked on getting my Search page working correctly. | 3 hrs - Worked on the look and feel of the page correct | 3 hrs - Worked on making sure all of the pages have the same look and feel
Week 15 | 4 hrs - Worked on getting my search results page formatted correctly with scrolling detail rows and a fixed header row. | 3 hrs - Worked on getting the Search table scrolling to work correctly | 3 hrs - Worked on getting the Search table scrolling to work correctly | 3 hrs - Worked on getting the Search table scrolling to work correctly | 3 hrs - Worked on trying to get the project to work correctly in AWS | 3 hrs - Worked on trying to get the project to work correctly in AWS | 5 hrs - Worked on getting all of the documentation added and Java Doc created. Created the required video. Worked on trying to fix an issue that popped up with the Add Trail page.
Week 16